## Cover Page
Toll Bill Generator
Product Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
| Name | Academy - Project solutions
Role
Signature
| Date | 2019-12-12
Release ID: QTAD-PBL / 2.0.0 / 30-Mar-2015 |  |  |  | C3: Protected
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Product Backlog Instructions C3: Protected Controlled Copy
Backlog Worksheet
This sheet has to be filled while doing "Create Product Backlog" task in the Initial Envisioning Phase.
The Product backlog worksheet contains a list of features/requirements that the business would want to implement in an application. This worksheet would continue to exist from the beginning to the end of the project. The Product Owner maintains it by adding, modifying, removing any of the items listed there. They can also change the priority of the items so long as they are not being worked by the team in the ongoing Sprint. Most of the re-ordering would happen just before the Sprint Planning meeting. To ensure this kind of continuous update, this worksheet could be re-visited during periodic intervals once during the release elaboration Phase and thereafter during the project execution. The changes to the Product backlog could be triggered from several sources in terms of inclusion of new features / bugs/ known issues based on the stakeholder requests and the effort, schedule for the same would also be re-visited in the product backlog worksheet. Fill the following fields in the product backlog worksheet for each feature.
| User Story ID | <Provide unique ID for each User story>
| User Story Name | <Provide the theme/name of the User story or a high level requirement> Eg: User login Registration Mail notification
| User Story Role | < Provide who would be end User of the User story>. Details of who would use that functionality Eg:End User Admin Teacher Conference attendee
| User Story Details | <Provide description of what the User want> Provide details on "As a/an" particular user what the user wants. Eg: As a conference attendee, I want to be able to register online
| Acceptance criteria | <Specify the Acceptance criteria> Acceptance criteria define the boundaries of a user story, and are used to confirm when a story is completed and working as intended. So for the above example, the acceptance criteria could include: A user cannot submit a form without completing all the mandatory fields Information from the form is stored in the registrations database.
| Sprint | Sprint in which the user story is planned to completed. Select it from the drop down. Story Point is given in Fibonacci series of upto 21. For any User story if the estimation goes beyond 21, then the user story has to be broken down.
| Story point | A story point is a metric used in agile project management and development to determine (or estimate) the difficulty of implementing a given story. Select the story point that will be assigned to the user story from the drop down (in Fibonacci series) during the sprint planning meeting while estimating an user story.
| Done | Yes/No field, that can be selected from drop down based on an user is completed or not
| Added in Sprint | Provide sprint number when the particular User Story was handled
| Closed in sprint | Provide sprint number when the particular User Story was completed
| Actual Story Points | Actual story point burned for an user story while developing. Select from the drop down (in Fibonacci series)
Charts
| Sprint | This value is non-editable. Represents the Sprint numbers
| Story Points remaining | Enter the total story points calculated for the Sprint.
| Done | Enter the total story points that was "Done" in the sprint
| Variation | This value is non-editable. Variation is calculated as [(Current sprint's story point remaining + done) - (Previous sprint's story point remaining + done) + Previous sprint's variation]
| Percent Complete | Percentage completed is calculated as [(Done story point of the sprint/(Done story point + story point remaining)) *100]
| Release Burn Down Chart | 1. A typical release Burn Down chart would enable the Product Owner to assess as to how each iteration is progressing towards realizing the release goal. They would be able to assess the number of features that are going to make it (or) not make it to the release based on the number of features delivered by the team in each iteration. 2. Based on the progress being made by the team, the Product Owner may decide to add more Sprints within a release (if it is a feature driven release) or cut down some of the features from the Release backlog (if it is a Date driven release). The release burn down chart would be automatically plotted based on the data given on the Release burn down table with story points remaining and the done.

## Backlog
Product Backlog Toll Bill Generator Project ID: B018 C3: Protected Controlled Copy
Done
User Story Id | User Story Name | User Story Role | User Story Details | Acceptance criteria | Sprint | Story Point | Done | Added in Sprint | Closed in sprint | Actual Story Points
US_1 | Initial Selection | Admin/Admin/User | As Users, we want to select the user type and Login/Registration option | 1- All Users should be provided with the option to select the user type -Admin, Admin,User 2-All users should have option to Login/Register | 1 | 1
US_2 | User Registration | User | As user I want the system to procure the fundamental details of the user | 1-When the user clicks on the registration link, it should re-direct to registration form. 2-User needs to fill some of the basic attributes/fields which are necessasary. 3-Clicking ‘Submit’ should validate the datatype constraints for each field 4-User failing to provide information on the mandatory fields be provided with an alert message – ‘Please update the highlighted mandatory field(s).’ Also, highlight the missed out field in red 5-User shouldn’t be allowed to register if the particular credentials like email is already present in database 6-Post-successful field level validation, save the information in the database 7-Upon saving the information in the database, display the message ‘Your details are submitted successfully’. | 1 | 3
US_3 | User Authentication | User | As User I want the system to authenticate the user credentials of the registered user | 1-A registered user – is able click ‘Login’ link, after keying in ‘UserID’ or ‘email’ & ‘Password’ field and get his credentials authenticated with the existing database entry. 2-If any problems during authentication user should be notified accordingly | 1 | 2
US_4 | Admin Registration | Admin | As Admin I want the system to procure the fundamental details of the admin | 1-The admin should be redirected to a different registeration page from that of user while registering 2-Admin needs to fill some of the basic attributes/fields which are necessasary. 3-Clicking ‘Submit’ should validate the datatype constraints for each field 4-Admin failing to provide information on the mandatory fields be provided with an alert message – ‘Please update the highlighted mandatory field(s).’ Also, highlight the missed out field in red 5-Post-successful field level validation, save the information in the database 6-Upon saving the information in the database, display the message ‘Your details are submitted successfully’. | 1 | 3
US_5 | Admin Authentication | Admin | As Admin I want the system to authenticate the admin credentials | 1-The registered admin should be able to login successfully with the id and password provided by the admin 2-If any problems during authentication user should be notified accordingly | 1 | 2
US_6 | Add and Modify Toll Details | Admin | As Admin I want the system to provide feature for admin to add a new toll plaza and modify the prices for that toll | 1-The Admin should be successfully able to add a new toll detail to the database 2-Admin should be able to modify the prices of journey of the particular existing toll | 1 | 3
US_7 | Provide Toll Details | User | As User I want the system to provide the details of the toll based on location searched by the user. | 1-On successful authentication the user should be landed to the home page. 2-The page should have the options to enter the “from” and “to” location 3-User should be able to select the from and to location from a drop down list 4-The system should provide the details of toll (if exists), for the location that the user had entered in the from and to field | 1 | 3
US_8 | Toll Bill Payment | User | As User I want the system to accept the bill amount and provide the proof | 1-The homepage should have feature for bill payment for desired toll 2-The user should have the feature for oneway or return payment 3-After Payment of the bill the users must be acknowledged for the bill they paid through message 4-After bill payment the users must successfully get the proof of bill payment | 1 | 5
US_9 | Modify Travel plan | User | As User I want to modify the travel plan | 1-User should have option to modify the from and to details after the payment is done 2-New toll details should be generated for the user 3-Only the Balance amount amount should be asked to pay from the user 4-Similarly, if the previously paid amount is higher than tha new toll details, the extra amount to be put back to the User's account 5-Modification should be done 24hrs before the expected travel plan | 2 | 8
US_10 | Delete Travel plan | User | As User I want to delete a travel plan | 1- User shuld have options to delete a travel plan 2-The paid amount should be returned to User 3-Cancellation should be done on the 24 hours before the expected travel plan | 2 | 5
US_11 | User Profile Modification | User | As user I want the system to provide feature for user to modify the profile | 1-The user should have the features for modification of the allowed attributes such as vehicle type and vehicle number etc | 2 | 3
US_12 | User feedback | User | As User I want to provide feedback on the usage of the service | 1- User should be able to provide feedback on the service used 2-Feedback should be in questionnaire form 3- Rating should be from 1 -5 | 2 | 2
US_13 | Admin Report | Admin | As Admin I want to generate report | 1-Admin should be able to generate report 2-Feedback should be downoaded in excel form 3-Report should have the details of the tolls, price of tolls, location, Admin details etc | 2 | 8
US_14 | Admin feedback report | Admin | As Admin I want to generate user feedback report | 1-Admin should be able to generate feedback report. 2-Feedback should be downoaded in excel form | 2 | 5
US_15 | Log off | Admin/User | As all user I want to log off | 1-Users should have options to logoff. | 1 | 1

## Charts
Release Burndown
Only edit shaded columns, others are calculated
Sprint | Story points |  |  | Percent Complete | Min | Max
| Remaining | Done | Variation
1 | 54 | 0 | 0 | 0% | 0 | 54
2 | 54 | 0 | 0 | 0% | 0 | 54
Yes
No

## Sheet1 (hidden)
0
5
10
20
30
50
80
130
200
400
1000